{"text_format":"3","workbook":"xls","n_sheets":2,"sheets":["办理流程","Sheet3"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"办理流程","index":0,"n_rows":16,"n_cols":6,"rows_kept":16,"merged":[[0,0,0,5],[15,0,15,5]],"flags":["formulas_cached_only"]}
["阳江市社会投资简易低风险工程办理流程清单"]
["序号","环节类型","环节名称","办理时间（天）","费用（元）","备注"]
[1,"行政许可","建设用地规划许可证核发（签订国有建设用地使用权出让合同）和企业投资项目备案并联办理",2,0]
[2,"第三方行为","编制评审文件（岩土试验报告编制、规划设计方案编制、规整报告编制）",25,"双方合同约定","自有土地项目或主动公开的地质信息初步勘察深度不满足设计要求的，由设计单位负责发包确定勘察单位开展岩土工程勘察工作，编制时间不超过10天，规划设计方案编制不超过10天，规整报告编制不超过5天。"]
[3,"技术审查及第三方行为","施工图设计文件审查（联合审图）",5,"双方合同约定"]
[4,"建设方行为","聘请监理",1,"双方合同约定"]
[5,"建设方行为","缴交农民工工资保证金",1,"施工合同总价的3%","缴存原则上不超过施工合同总价的3%,且最高不超过300万元"]
[6,"第三方行为","获取供水接入服务",4,0]
[7,"第三方行为","获取供电接入服务",4,0]
[8,"行政许可","建设工程规划许可和施工许可阶段事项并联办理",5,"按规定缴交城市基础设施配套费","《关于调整市区房地产开发及公建项目规划报建税费计算基数有关事项的通知》(阳住建〔2018〕13号)"]
[9,"行政许可","开工前首次工程质量安全监督检查",1,0]
[10,"行政许可","施工过程中一次工程质量安全监督检查",1,0]
[11,"第三方行为","联合测绘（规划条件核实测量、不动产测量）",5,"双方合同约定"]
[12,"行政许可","竣工联合验收（建设五方责任主体竣工验收和政府部门验收一次性完成）",4,0]
[13,"行政许可","不动产登记（国有建设用地使用权及房屋所有权登记）",1,550]
["社会投资简易低风险工程建设项目办理建筑许可环节为13个，其中行政审批环节6个，技术审查及第三方行为环节7个，全流程办理时间压减为60天以内，其中行政审批时间不超过15天，技术审查及第三方行为不超过45天。"]

{"sheet":"Sheet3","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}